## Sheet1
ProjectID | AptID | ProjectName | Description | Category | Status | RequestedDate | ScheduledDate | CompletedDate | CompletionTime | Quarter
4001 | 1001 | Carpentry Project | Repairing and enhancing wooden structures | Carpentry | Completed | 2023-10-10 | 2023-10-11 | 2023-10-12 | 4 | 4
4002 | 1002 | Plumbing Upgrade | Upgrading plumbing fixtures and pipes | Plumbing | Completed | 2023-10-11 | 2023-10-12 | 2023-10-16 | 8 | 4
4003 | 1003 | Maintenance Task | Repairing mechanical systems and appliances | Mechanical and Appliance Repair | Completed | 2023-10-12 | 2023-10-13 | 2023-10-16 | 7 | 4
4004 | 1004 | Appliance Checkup | Routine checkup and maintenance of appliances | Mechanical and Appliance Repair | Completed | 2023-10-13 | 2023-10-14 | 2023-10-14 | 2 | 4
4005 | 1005 | Pest Control Service | Extermination and prevention of pest infestations | Pest Control | Completed | 2023-10-14 | 2023-10-15 | 2023-10-17 | 4 | 4
4006 | 1006 | Window Replacement | Installing energy-efficient windows | Carpentry | Completed | 2023-10-15 | 2023-10-16 | 2023-10-22 | 12 | 4
4007 | 1007 | Mice Control | Implementing measures to control and prevent mice infestation | Pest Control | Completed | 2023-10-16 | 2023-10-17 | 2023-10-17 | 1 | 4
4008 | 1008 | Leak Detection | Service for detecting and fixing hidden leaks | Plumbing | Completed | 2023-10-17 | 2023-10-18 | 2023-10-23 | 10 | 4
4009 | 1009 | Roof Repair | Patching and fixing leaks in the roof | Carpentry | Completed | 2023-10-18 | 2023-10-19 | 2023-10-22 | 6 | 4
4010 | 1010 | Outdoor Painting | Repainting the exterior of the building | Carpentry | Completed | 2023-10-19 | 2023-10-20 | 2023-10-27 | 14 | 4
4011 | 1011 | Heating System Checkup | Routine checkup and maintenance of heating system | Mechanical and Appliance Repair | Completed | 2023-10-20 | 2023-10-21 | 2023-10-22 | 3 | 4
4012 | 1012 | Garage Door Replacement | Installing a new garage door | Carpentry | Completed | 2023-10-21 | 2023-10-22 | 2023-10-24 | 5 | 4
4013 | 1013 | Plumbing Repairs | Fixing plumbing issues in the kitchen and bathroom | Plumbing | Completed | 2023-10-22 | 2023-10-23 | 2023-10-28 | 11 | 4
4014 | 1014 | Deck Restoration | Refurbishing the outdoor deck | Carpentry | Completed | 2023-10-23 | 2023-10-24 | 2023-10-24 | 3 | 4
4015 | 1015 | Electrical Rewiring | Rewiring outdated electrical systems | Carpentry | Completed | 2023-10-24 | 2023-10-25 | 2023-10-25 | 4 | 4
4016 | 1016 | Appliance Upgrade | Replacing old appliances with new, energy-efficient models | Mechanical and Appliance Repair | Completed | 2023-11-07 | 2023-11-08 | 2023-11-10 | 5 | 4
4017 | 1017 | Gutter Cleaning | Removing debris and cleaning gutters | Carpentry | Completed | 2023-11-08 | 2023-11-09 | 2023-11-10 | 3 | 4
4018 | 1018 | Bathroom Tile Replacement | Upgrading bathroom tiles | Carpentry | Completed | 2023-11-09 | 2023-11-10 | 2023-11-10 | 2 | 4
4019 | 1019 | Flea and Tick Treatment | Treating for fleas and ticks in the apartment | Pest Control | Completed | 2023-11-10 | 2023-11-11 | 2023-11-15 | 7 | 4
4020 | 1020 | Security System Installation | Installing a new security system | Carpentry | Completed | 2023-11-11 | 2023-11-12 | 2023-11-18 | 15 | 4
4021 | 1021 | Water Heater Replacement | Replacing old water heaters with new, efficient models | Plumbing | Completed | 2023-11-12 | 2023-11-13 | 2023-11-15 | 5 | 4
4022 | 1022 | Attic Insulation | Improving insulation in the attic | Carpentry | Completed | 2023-11-13 | 2023-11-14 | 2023-11-14 | 2 | 4
4023 | 1023 | Fireplace Maintenance | Routine maintenance of the fireplace | Carpentry | Completed | 2023-11-14 | 2023-11-15 | 2023-11-15 | 1 | 4
4024 | 1024 | Mosquito Control | Applying measures to control and prevent mosquito infestation | Pest Control | Completed | 2023-11-15 | 2023-11-16 | 2023-11-17 | 6 | 4
4025 | 1025 | Cockroach Extermination | Exterminating cockroaches and implementing preventive measures | Pest Control | Completed | 2023-11-16 | 2023-11-17 | 2023-11-22 | 17 | 4
4026 | 1026 | Ant Control | Eliminating ant infestation and blocking entry points | Pest Control | Completed | 2023-11-17 | 2023-11-18 | 2023-11-18 | 2 | 4
4027 | 1027 | Wasp Nest Removal | Removing and relocating wasp nests | Pest Control | Completed | 2023-11-18 | 2023-11-19 | 2023-11-22 | 9 | 4
4028 | 1028 | Cabinet Refinishing | Refinishing kitchen cabinets | Carpentry | Completed | 2023-11-19 | 2023-11-20 | 2023-11-24 | 10 | 4
4029 | 1029 | Staircase Repair | Fixing and reinforcing the staircase | Carpentry | Completed | 2023-11-20 | 2023-11-21 | 2023-11-25 | 12 | 4
4030 | 1030 | Roof Inspection | Inspecting and assessing the condition of the roof | Carpentry | Completed | 2023-11-21 | 2023-11-22 | 2023-11-24 | 11 | 4
4031 | 1031 | Door Replacement | Replacing old doors with new ones | Carpentry | Scheduled | 2023-12-03 | 2023-01-01 | NULL | NULL | 4
4032 | 1032 | Spider Extermination | Exterminating spiders and sealing entry points | Pest Control | Scheduled | 2023-12-04 | 2023-01-02 | NULL | NULL | 4
4033 | 1033 | Home Theater Installation | Setting up a home theater system | Carpentry | Scheduled | 2023-12-05 | 2023-01-03 | NULL | NULL | 4
4034 | 1034 | Pipe Inspection | Inspecting and assessing the condition of pipes | Plumbing | Scheduled | 2023-12-06 | 2023-01-04 | NULL | NULL | 4
4035 | 1035 | Water Heater Repair | Repairing issues with the water heater | Plumbing | Scheduled | 2023-12-07 | 2023-01-05 | NULL | NULL | 4
4036 | 1036 | Kitchen Sink Replacement | Replacing the kitchen sink and associated plumbing | Plumbing | Scheduled | 2023-12-08 | 2023-01-06 | NULL | NULL | 4
4037 | 1037 | Plumbing Fixture Upgrade | Upgrading plumbing fixtures throughout the apartment | Plumbing | Scheduled | 2023-12-09 | 2023-01-07 | NULL | NULL | 4
4038 | 1038 | Pipe Sealing | Sealing and preventing leaks in pipes | Plumbing | Scheduled | 2023-12-10 | 2023-01-08 | NULL | NULL | 4
4039 | 1039 | Appliance Maintenance | Routine maintenance of household appliances | Mechanical and Appliance Repair | Scheduled | 2023-12-11 | 2023-01-09 | NULL | NULL | 4
4040 | 1040 | HVAC System Checkup | Routine checkup and maintenance of the heating, ventilation, and air conditioning (HVAC) system | Mechanical and Appliance Repair | Scheduled | 2023-12-12 | 2023-01-10 | NULL | NULL | 4
4041 | 1041 | Washing Machine Repair | Repairing issues with the washing machine | Mechanical and Appliance Repair | Scheduled | 2023-12-13 | 2023-01-11 | NULL | NULL | 4
4042 | 1042 | Refrigerator Upgrade | Upgrading and installing a new refrigerator | Mechanical and Appliance Repair | Scheduled | 2023-12-14 | 2023-01-12 | NULL | NULL | 4
4043 | 1043 | Rodent Extermination | Exterminating rodents and sealing entry points | Pest Control | Scheduled | 2023-12-15 | 2023-01-13 | NULL | NULL | 4
4044 | 1044 | Termite Inspection | Inspecting for termites and applying preventive measures | Pest Control | Scheduled | 2023-12-16 | 2023-01-14 | NULL | NULL | 4
4045 | 1045 | Bed Bug Treatment | Eradicating bed bugs from the apartment | Pest Control | Scheduled | 2023-12-17 | 2023-01-15 | NULL | NULL | 4